# RefexOne – Flutter Migration (Web, Android, iOS)

Migration Assessment, Disadvantages and Risk Analysis

| Item | Value |
| --- | --- |
| Document | Migration Assessment and Risk Analysis |
| Version | 2.1 (draft for review) |
| Date | 30-Oct-2026 |
| System | RefexOne (refexone.com) – IAM launcher, SSO identity provider, Help Desk (ITSM), Refexions chat |
| Source reviewed | super-app repo, branch itsmbackuplatest, commit 2184f48; docs/FLOW_RUNBOOK.md flows F01–F15 |
| Change type | Frontend only. Backend (FastAPI + MongoDB) stays unchanged. |
| Companion document | RefexOne_Flutter_BRD.docx |
| Status | Analysis only. No code was changed in RefexOne, Notification Engine or aasik_ITSM. |

# Contents

Contents are built when the document opens in Word (choose Yes to update fields).

# 1. Executive summary

Question. Can RefexOne move its frontend to Flutter for Web, Android and iOS without changing the backend, and what does it cost, risk and change?

Feasibility. Yes, technically feasible with zero backend code change. Three non-code items are needed (static App-Link files on the web server if phone login uses the system browser, optional Azure/Google redirect entries, and the existing store signing keys).

Size. Full rewrite: 25 screens, about 18,000 lines of React UI and 46 shared UI components. Nothing is reused.

What does not become native. Kissflow, Adrenalin and NE Reports are web apps; they still open as web pages inside the Flutter app. SP-initiated SAML (Kissflow sending users to the RefexOne login page) works only in the web build.

Live updates. Today both phone apps open refexone.com, so a web deploy updates phones within minutes. After Flutter, every phone UI change needs a new build, store review and users updating (hours to 3 days). Web stays instant.

Risks. 20 risks: 3 High (login/SSO regression at cutover, loss of instant phone updates, hidden frontend rules missed in the rewrite), 11 Medium, 6 Low.

Recommendation. Run a 2-week proof gate first. Then choose Option B (Flutter phone apps, web stays React, about 14–16 weeks) unless one codebase for the web admin consoles is a firm requirement, in which case Option C (full Flutter, about 23–25 weeks).

The requirements themselves are in the companion BRD.

# 2. Current system and rebuild size

| Layer | Today |
| --- | --- |
| Web frontend | React 19, Create React App + craco, Tailwind, Radix/shadcn (46 shared UI components), react-router 7, axios. 25 page files (about 15,800 lines) plus 5 feature components (about 2,400 lines). Served by Nginx from frontend/build on the production server (/opt/superapp). |
| Backend | FastAPI (server.py about 4,400 lines + routes azure_ad, google_oauth, itsm, refexions, scim, user_master), uvicorn :8001 behind Nginx, MongoDB, APScheduler (Adrenalin HR sync), SMTP mail. |
| Android app | Capacitor 6 BridgeActivity, package com.refex.refexone, version 1.0.10 (build 10), minSdk 22, target 36. Loads https://refexone.com live. Native extras: per-domain Kissflow cookie clearing, RefexOneBridge (clear Kissflow session, open Adrenalin app, open external URL), Play Store intents, force-update check GET /api/app-update/check. |
| iOS app | Swift WKWebView app (RefexSuperApp), bundle com.refex.refexone (live) and com.refex.refex (Superapp listing), version 1.0.10 (10), iOS 15+. Loads https://refexone.com live, same update check and Kissflow session handling. |
| Web extras | sw.js service worker (network-first, HTML never cached), manifest.json (PWA install), privacy-policy.html, Google site-verification file, icons, setup-guide HTML pages. |
| Auth token | JWT in localStorage (iam_token) and cookie iam_token on refexone.com. Backend reads the Bearer header, a ?token= query, or the cookie (cookie resumes SP-initiated SAML). |

## 2.1 Screens to rebuild

| Screen / component | Lines | Main API groups | Audience |
| --- | --- | --- | --- |
| Login (/login, /developerlogin) | 594 | auth, azure-ad/providers, google-oauth/providers | All |
| AppLauncher (/launcher) | 955 | launcher/apps, itsm/kissflow-status, SAML complete, OIDC | All |
| RefexionsChat (launcher widget) | 926 | refexions/*, itsm/* | All |
| AppCatalog (/catalog) | 141 | catalog/apps, access-requests | All |
| AccessRequests (/access-requests, /requests) | 132 | access-requests | User + Admin |
| AppDownload (/download, public) + RefexOneAppDownload | 134 + 183 | app-download/links | Public |
| Layout (header, profile, password, photo) | 610 | users/me, auth/change-password, upload | All |
| ITSMDashboard (/itsm) | 2,559 | itsm/reports, comments, rating, reopen, attachments | All |
| CreateITRequest (/itsm/new) | 1,622 | itsm/config, approval-matrix, locations, tickets | All |
| CommentAttachmentPreview | 587 | itsm/reports attachment-preview | All |
| Dashboard (/) | 132 | dashboard/stats | Admin |
| Users | 1,416 | users, apps, groups, roles, kissflow-scim/link-user, export | Admin |
| Groups / Roles / Policies | 266 / 206 / 309 | groups, roles, permissions, policies | Admin |
| SAMLApps / OIDCApps | 768 / 934 | apps/saml, apps/oidc, upload/logo | Admin |
| MobileApps (/apps/mobile, /settings/app-update) | 539 | apps/mobile, app-update/config | Admin |
| AuditLogs | 202 | audit-logs | Admin |
| HRSync | 170 | hr-sync | Admin |
| SCIMSetup | 726 | scim/tokens, kissflow-scim, user-master | Admin |
| ITSMSetup | 1,077 | itsm/admin/*, config/environments | Admin |
| RefexionsSetup | 829 | refexions/admin | Admin |
| AzureADSetup / GoogleSetup | 494 / 655 | azure-ad/*, google-oauth/* | Admin |
| Settings | 149 | org, upload/logo | Admin |
| SAMLConfig / OIDCConfig | 391 / 429 | saml/config, oidc/config | Not routed in App.js today – confirm if still needed |

# 3. Migration assessment

## 3.1 Assessment method

Each area was scored on four factors from the code and the flow runbook: Complexity (size and logic), Web dependency (how much of the flow must stay in a browser), Native gain (benefit of going native) and Test effort. The verdict says how the area should be migrated.

## 3.2 Assessment by functional area

| Flow | Area | Complexity | Web dependency | Native gain | Test effort | Verdict |
| --- | --- | --- | --- | --- | --- | --- |
| F01 | Login and session | High | High (OAuth and SSO redirects) | Medium (biometrics, secure storage) | High | Migrate after Phase 0 proof |
| F02 | Profile, password, photo | Low | None | Medium (camera) | Low | Ready to migrate |
| F03 | App Launcher (tiles, search, Reports tabs) | High | High (all launches are SSO) | Low | High | Migrate UI; launches use web view |
| F04 | Catalog and access requests | Low | None | Low | Low | Ready to migrate |
| F05 / F06 | SAML and OIDC launch (Kissflow, Adrenalin, NE Reports) | High | Full (browser POST by protocol) | None | High | Web view only |
| F07 | Admin IAM (users, groups, roles, policies, audit) | Medium-High (dense tables) | None | Low | Medium | Web-first; phone usable but secondary |
| F08 / F09 | HR sync, SCIM, User Master | Medium | None | None | Medium | Web-first |
| F10 | Help Desk (list, create, comments, files) | High (about 4,800 lines) | None | High (camera, offline, notifications) | High | Best candidate for native |
| F11 | ITSM Setup (production-sensitive keys) | Medium | None | None | Medium | Web-first, extra confirmations |
| F12 | Refexions chat and voice | Medium | None | Medium (native voice) | Medium | Ready to migrate |
| F13 | Azure AD and Google admin | Medium | None | None | Medium | Web-first |
| F14 | Mobile apps, force update, download page | Low | None | High | Medium | Ready to migrate |
| F15 | Organisation settings | Low | None | None | Low | Ready to migrate |

## 3.3 Readiness of the current system

| Factor | Finding | Effect on migration |
| --- | --- | --- |
| API design | Clean REST + Bearer token for every screen | Positive – frontend can be replaced without backend work |
| Business rules location | Most rules (access, SSO, ITSM, mail) live in the backend | Positive – less logic to re-write |
| Frontend-only rules | Launcher visibility helpers (RMC P2P, Procure-to-Pay, Reports chief-title), Kissflow fallback rules, Safari tab handling, Kissflow deep-link polling, voice helpers | Must be ported exactly; covered by risk R03 |
| Native shell code | Android MainActivity (about 1,100 lines Java) and iOS WebViewController (Swift) hold cookie, bridge and update logic | Must be re-implemented in Flutter plugins |
| Tests | Backend pytest suites per flow; frontend Playwright and launcher unit tests | Backend tests reused unchanged; frontend tests rewritten |
| Documentation | FLOW_RUNBOOK F01–F15 checklists and P0 smoke suite | Strong – used as acceptance criteria |
| Release process | Web: yarn build on server. Mobile: manual Xcode/Gradle builds, public App Store rules in runbook section 8 | Needs CI for three platforms |
| Team skills | JavaScript/React today | Dart/Flutter training or hiring needed |

## 3.4 Overall assessment

| Question | Answer |
| --- | --- |
| Technically feasible? | Yes |
| Backend change needed? | No |
| Can all functions be kept? | Yes, but SSO apps remain web views and SP-initiated SAML remains web-only |
| Main blockers | None hard; highest risks are login/SSO cutover and release cadence |
| Recommended option | B (mobile in Flutter, web stays React) unless one web codebase is mandatory (then C) |

# 4. Backend-unchanged verification

Verified against the code: no backend code change is required.

| Area | Why it works unchanged | Frontend requirement |
| --- | --- | --- |
| All REST APIs | Bearer JWT in the Authorization header | API client with a token interceptor; base URL https://refexone.com/api |
| CORS | Flutter Web is served from refexone.com; native apps are not subject to CORS | Host the Flutter web build on the same domain |
| Password login | POST /api/auth/login returns the JWT | Keychain/Keystore on mobile; localStorage + iam_token cookie on web |
| Microsoft / Google login | Callback already redirects to https://refexone.com/login?azure_token= / google_token= (or *_error) | Web: same /login route. Mobile: read the token from an in-app web view (as today) or system browser + App Links |
| SP-initiated SAML (Kissflow to RefexOne) | Backend sends the browser to /login?sso_app=&relay_state= and resumes with the iam_token cookie | Flutter Web keeps the same /login params and sets the cookie exactly as today |
| IdP-initiated SAML (launcher to Kissflow / Adrenalin) | /api/saml/{id}/complete?token= returns an auto-POST page | Open it in an in-app web view (mobile) or a new tab (web) |
| OIDC apps and NE Reports | /api/oidc/{id}/authorize, then code and token | Same launch URL with embed=1, return_to, user_name, user_title |
| Force update | /api/app-update/check?platform=&build= and admin config | Call on start with the new build number |
| File uploads | Multipart endpoints | Native camera/file picker; same 5 MB rule |
| Refexions | REST endpoints; voice is client-side | Native speech plugin on mobile, browser speech on web |

## 4.1 Non-code items still required

| Item | Needed when | Owner |
| --- | --- | --- |
| /.well-known/apple-app-site-association and /.well-known/assetlinks.json as static files on refexone.com | Only if phone login uses the system browser + App Links | Web server / DevOps |
| Extra redirect URI in Azure App Registration / Google Cloud client | Only if a new redirect address is chosen | IT admin (console setting) |
| Existing Android signing key and Apple team certificates | Always | Mobile release owner |
| Store listing updates (screenshots, privacy labels, public-listing wording) | Always | Mobile release owner |

# 5. Advantages

| Advantage | Benefit |
| --- | --- |
| One codebase | Dart code for Web, Android and iOS replaces React + Java shell + Swift shell |
| Native performance | Smoother scrolling, faster start, consistent look on every device |
| Native features | Biometric unlock, secure token storage, camera upload, offline handling |
| Store safety | Lower risk of App Store rejection than a website wrapper (guideline 4.2) |
| Cleaner native layer | Removes the separate cookie/bridge code in Java and Swift |
| Responsive by design | One widget tree adapts from 320 px phones to desktops |

# 6. Disadvantages (detailed)

## 6.1 Business

| Disadvantage | Impact |
| --- | --- |
| Large investment with no new features | 14–25 weeks of work only to reach parity with what exists today |
| Slower fixes on phones | A text or field fix that is live in minutes today takes 1–3 days through the stores |
| Two products to run during the transition | React and Flutter both need bug fixes until cutover is complete |
| Store dependency | Releases depend on Apple and Google review; App Store has already pushed RefexOne towards unlisted distribution once (runbook section 8) |

## 6.2 Technical

| Disadvantage | Impact |
| --- | --- |
| No code reuse | About 18,000 lines of React screens and 46 UI components are rewritten in Dart |
| Web views remain | Kissflow, Adrenalin and NE Reports still open as web pages inside the app; the main launcher action does not become native |
| SP-initiated SAML is web-only | The web build must keep exactly the same /login contract and cookie |
| Flutter Web limitations | Larger first download than React, text selection and browser search need extra work, dense admin tables are harder |
| Native logic re-implemented | Kissflow cookie clearing, Adrenalin hand-off, update check and navigation rules move from Java/Swift into Flutter plugins |
| Third-party plugin dependency | Web view, speech, file picker and secure-storage plugins must keep up with OS updates |
| Tests rewritten | Playwright and frontend unit tests no longer apply |

## 6.3 Operational

| Disadvantage | Impact |
| --- | --- |
| Release management for three targets | Signing keys, version numbers, store listings, review notes and staged rollouts for every release |
| Many app versions in the field | Users on older builds keep old screens until they update; support must know which version a user has |
| CI/CD needed | Automated Android, iOS and Web builds instead of a single server build |

## 6.4 Users

| Disadvantage | Impact |
| --- | --- |
| Update prompts | Users must install updates to get fixes; forced updates interrupt work |
| Older Android phones | Android 5.1–6 devices may stop receiving updates |
| Visual and interaction changes | Even with the same design, some screens will feel different; short guidance needed |

# 7. Live UI updates and release management

## 7.1 Today

| Platform | How a UI change reaches users | Time |
| --- | --- | --- |
| Web | git pull + yarn build on the server; service worker never caches the HTML | Minutes |
| Android | App opens refexone.com in a web view, so the same web deploy updates it; store build only for shell changes | Minutes |
| iOS | Same – WKWebView loads refexone.com live | Minutes |

## 7.2 After Flutter

| Platform | How a UI change reaches users | Typical time |
| --- | --- | --- |
| Web | Build Flutter web and copy to the server; set no-cache on index.html and bootstrap files | Minutes |
| Android | New AAB (versionCode +1), Play Console upload, review, staged rollout, users update | Hours to 2–3 days |
| iOS | New IPA (build +1), App Store Connect upload, App Review, release, users update; follow runbook section 8 | 1–3 days, longer if rejected |

## 7.3 Ways to reduce the impact (no backend code change)

| Option | What it does | Notes |
| --- | --- | --- |
| Existing force-update gate | Admin sets the minimum build in /settings/app-update; older builds are blocked with a store link | Already in the backend |
| Android in-app updates | Prompts and installs updates inside the app | Frontend plugin only |
| Code push (for example Shorebird) | Sends Dart code patches to installed apps without store review, within store rules | Paid service; native/plugin changes still need a store build |
| Remote config / feature flags | Switch features or texts without a build | Client-side service such as Firebase Remote Config |
| Keep fast-changing screens as web views | Admin consoles or reports stay web and update instantly | This is Option B |

## 7.4 Versioning rules

Continue from 1.0.10 / build 10 (for example 2.0.0 / build 11) on the same package and bundle IDs so stores treat it as an update.

Sign Android with the existing upload key (Play App Signing); otherwise current users cannot update.

Keep both iOS records (com.refex.refexone live, com.refex.refex Superapp) and the public-listing rules.

# 8. Risk analysis

## 8.1 Method

Likelihood (L) and Impact (I) are scored 1 (very low) to 5 (very high). Score = L x I. Rating: High 15–25, Medium 8–14, Low 1–7.

## 8.2 Risk register

| ID | Category | Risk | L | I | Score | Rating | Mitigation | Contingency | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R01 | Login / SSO | Login or SSO breaks at cutover (Microsoft, Google, SAML, OIDC) | 3 | 5 | 15 | High | Phase 0 proof gate; F01/F05/F06 checklists on all platforms; parallel run | Roll web back to React build; halt mobile rollout; 1.0.10 keeps working | Tech lead |
| R02 | Release | Loss of instant UI updates slows urgent fixes | 5 | 3 | 15 | High | Force-update gate, Android in-app updates, code push, hybrid web views | Hotfix through expedited App Review | Product owner |
| R03 | Scope | Hidden frontend rules missed in 18k lines (launcher visibility, Kissflow fallbacks, Safari handling, deep-link polling) | 4 | 4 | 16 | High | Code walkthrough per screen; requirement-to-checklist mapping; parity testing with same accounts | Fix in next release; keep React live until parity signed off | Business analyst |
| R04 | Login | Google blocks sign-in inside embedded web views | 3 | 4 | 12 | Medium | System browser + App Links for Google on mobile | Temporarily route Google login to web | Mobile lead |
| R05 | Login | Microsoft conditional-access policy blocks embedded sign-in | 2 | 4 | 8 | Medium | System browser option; test with each tenant | Same as R04 | Mobile lead |
| R06 | SSO | Kissflow session or cookie handling differs (wrong user, logout not clearing) | 3 | 4 | 12 | Medium | Web-view plugin with per-domain cookie control; multi-user device tests | Force clear all web-view cookies on logout | Mobile lead |
| R07 | SSO | SP-initiated SAML breaks if Flutter Web changes /login params or the iam_token cookie | 2 | 5 | 10 | Medium | Contract tests for the integration contracts (BRD section 8); same cookie flags | Restore React login page | Web lead |
| R08 | Store | App Store rejection (unlisted request, guideline 4.2, privacy labels) delays launch | 3 | 4 | 12 | Medium | Follow runbook section 8; early TestFlight review | Keep current 1.0.10 live | Release owner |
| R09 | Performance | Flutter Web slow on admin screens (first load, large tables) | 4 | 3 | 12 | Medium | Deferred loading, WebAssembly build, paged tables; measure against React baseline | Keep admin on React (Option B) | Web lead |
| R10 | Schedule | Effort overruns 23–25 week estimate | 4 | 3 | 12 | Medium | Phased delivery; user flows first; fixed parity scope | Release mobile user flows first, admin later | Project manager |
| R11 | People | Dart/Flutter skills gap | 3 | 3 | 9 | Medium | Training, senior Flutter developer, code reviews | External Flutter support | Engineering manager |
| R12 | Operations | Dual maintenance of React and Flutter during transition | 5 | 2 | 10 | Medium | Freeze new React features; short transition window | Prioritise fixes by platform | Project manager |
| R13 | Technical | Third-party plugins break on OS updates (web view, speech, file picker) | 3 | 3 | 9 | Medium | Use well-maintained plugins; test on OS betas | Pin versions; patch locally | Mobile lead |
| R14 | Security | Token or session regression (storage, mixed content) | 2 | 4 | 8 | Medium | Secure storage; remove cleartext; security review before release | Force logout via token expiry | Security owner |
| R15 | Release | Wrong signing key or bundle ID creates a second app instead of an update | 1 | 5 | 5 | Low | Release checklist; same IDs and Play App Signing | Re-sign and resubmit | Release owner |
| R16 | Compatibility | Android 5.1–6 devices unsupported | 2 | 2 | 4 | Low | Check device inventory | Keep 1.0.10 available for them | Product owner |
| R17 | Scope | A backend change becomes needed (for example push notifications) | 2 | 3 | 6 | Low | Keep push optional; Phase 0 proof | Separate approved backend change | Tech lead |
| R18 | Usability | Flutter Web text selection / browser search issues (copy ticket IDs, Ctrl+F) | 3 | 2 | 6 | Low | SelectionArea, copy buttons, semantics | Keep admin on React | Web lead |
| R19 | Integration | NE Reports tiles lose return_to / user_name params | 2 | 3 | 6 | Low | Contract tests for NE launch URL | Hotfix launch URL | Web lead |
| R20 | Adoption | Users need guidance for changed screens | 2 | 2 | 4 | Low | Same design language; short release notes | Help-desk FAQ | Product owner |

## 8.3 Risk summary

| Rating | Count | Risks |
| --- | --- | --- |
| High | 3 | R01, R02, R03 |
| Medium | 11 | R04 to R14 |
| Low | 6 | R15 to R20 |

## 8.4 Risk heat map (count of risks)

| Likelihood \ Impact | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 5 | 0 | 1 | 1 | 0 | 0 |
| 4 | 0 | 0 | 2 | 1 | 0 |
| 3 | 0 | 1 | 2 | 3 | 1 |
| 2 | 0 | 2 | 2 | 2 | 1 |
| 1 | 0 | 0 | 0 | 0 | 1 |

# 9. Options

| Option | Description | Backend change | Instant UI updates | Effort | Risk |
| --- | --- | --- | --- | --- | --- |
| A | Keep React web and current shells; add native plugins (biometrics, secure storage, file picker) | None | Kept everywhere | Low (weeks) | Low |
| B | Flutter for Android/iOS user screens (login, launcher, ITSM, Refexions, profile); web views for SSO apps; refexone.com and admin stay React | None | Kept on web; lost for native mobile screens | Medium (about 14–16 weeks) | Medium |
| C | Full Flutter for Web + Android + iOS, all screens | None | Web only | High (about 23–25 weeks) | High |

# 10. Delivery plan (estimate: 2 Flutter developers, 1 QA, part-time designer)

| Phase | Content | Exit criteria | Estimate |
| --- | --- | --- | --- |
| 0. Proof gate | Password, Microsoft and Google login; one Kissflow SAML app with module deep link; Adrenalin; one NE Reports tile with return_to; force-update check – on Android, iOS and Web with zero backend change | All pass on real devices; go / no-go decision | 2 weeks |
| 1. Foundation | Design system, responsive scaffold, routing with clean URLs, API client, auth/session, secure storage, error handling, CI for three platforms | Signed internal builds | 3 weeks |
| 2. User core | F01 login, F02 profile, F03 launcher + SSO, F04 catalog, F14 download | F01–F04 checklists pass on three platforms | 4 weeks |
| 3. Help Desk + Refexions | F10 list/create/comments/attachments/rating/reopen, F12 chat + voice | F10 (Refex and Non-Refex) and F12 checklists pass | 5 weeks |
| 4. Admin consoles (Option C only) | F05–F09, F11, F13–F15 admin screens | Admin checklists pass on web; usable on tablet | 6–8 weeks |
| 5. Hardening and release | Performance, accessibility, security review, UAT, store submission, web cutover | P0 suite + full F01–F15 pass; stores approved | 3 weeks |
| Total |  | Option C about 23–25 weeks; Option B about 14–16 weeks |  |

# 11. Cutover and rollback

Web: deploy Flutter web to a staging host; switch Nginx only after UAT; keep the React build for one-step rollback.

Mobile: staged rollout (Android 10 % to 50 % to 100 %; iOS phased release); keep 1.0.10 working; raise the force-update minimum only after the new build is stable.

Rollback: web – point Nginx back to the React build; mobile – halt rollout. Users on 1.0.10 keep working because the backend is unchanged.

# 12. Decisions needed

Option B (Flutter phone apps, web stays React) or Option C (full Flutter)?

Phone Microsoft/Google login: in-app web view (same as today) or system browser + App Links (more robust, needs two static files on refexone.com)?

Budget for a code-push service to soften the loss of instant phone updates?

Accept dropping Android 5.1–6 devices?

Prepared from a read-only review. No code in RefexOne, Notification Engine or aasik_ITSM was changed.